## 27-Aug
Sl. No. | Bug_id | Type | Time Estimate | Bug_description | Priority | Status | QA Status | Comments
1 | US_001 | Enhancement |  | Home page needs to be designed |  |  |  | Home page and Gym are the same currently, home page can have summations, events.
2 | US_002 | Enhancement |  | Logo placeholder needs to be there |  |  |  | From Usability point of view good to have it on the upper left of the screen.
3 | US_003 | Defect | 1 | Gym- Text and images to also be hyperlinks | P1
4 | US_004 | Defect |  | Clicking on "Launch next module", click on "Review", app crashes. | P1 | Fixed | Verified | Due to this links in skill review will not function
5 | US_005 | Defect |  | Clicking on "Launch next module", clicking on "Play Next" does nothing. | P1 | Fixed | Verified
6 | US_006 | Enhancement |  | Header and footer modules
7 | US_007 | Enhancement | 1 | need other modules and placeholders in the page like motivators, stars, an overall performance indicator etc. | P0 |  |  | Pie chart with peer percentile in the center. Add modules completed in a table below the skills for now.
8 | US_008 | Defect | 1 | description shows up in skill matrix - when one clicks on launch next module | P1
9 | US_009 | Defect |  | Skills not getting updated on new users creation. | P1 | Fixed | Verified
10 | US_010 | Defect |  | Event added not showing up in user's events | P1 | Fixed | Verified | Not a bug. Get updated once trainer accepts the invite
ADMIN module
1 | AD_001 | Defect |  | When creating users - Role field not editable or drop down present. | P1 | Fixed | Verified
2 | AD_002 | Defect |  | User is able to edit the role field, he should not be able to. | p1 | Fixed
3 | AD_003 | Defect |  | No submit button in edit skill page | P1 |  |  | contentadmin
4 | AD_004 | Defect |  | not able to edit existing users & cannot block users. | P2 |  |  | enable for hr admin too
EVENTS
1 | EV_001 | Defect |  | filter results - on change does not work, while adding users to event | P1
2 | EV_002 | Defect |  | If billing is not set, invite trainer button fails | P2
3 | EV_003 | Enhancement |  | In 1st place trainer module should not have option to edit billing rate. Hr_Admin should have option to update billing rate when creating a trainer.
4 | EV_004 | Enhancement |  | Any mail sent to hr_admin when trainer accepts or rejects an invite.Do we have SMS facility?
5 | EV_005 | Enhancement |  | real time notification updates… | P3
CONTENT ADMIN
1 | CA_001 | Defect |  | Labels while uploading content needs to be thr | P1/P2
2 | CA_002 | Defect |  | Description field needs to be added in Upload content | P1
3 | CA_003 | Defect |  | drop-down for add test in content admin for edit content. | P1 |  |  | Convert to drop-down
4 | CA_004 | Enhancement |  | Mandatory fields needs to be marked in forms | P2
5 | CA_005 | Defect |  | When tagging questions, the Tag Business intelligence always was getting added. | P3
REPORT_CARD
1 | RE_001 | Defect |  | Ratings values have been hard-coded needs to be dynamic | P1 | Fixed
SEND MAIL
1 | MAIL_001 | Enhancement |  | New user creation - in email text link(http://talentify.in:3000.) has to be a hyperlink, needs to be handled. | P1 |  |  | Convert lePo to Ilab in the email text
2 | MISC_002 | Enhancement |  | Date and time field needs to be validated and date picker needs to be implemented. | P1/P2
3 | MISC_003 | Enhancement |  | Sorting needs to be implemented across the application in List view. | P1/P2

## 28-Aug
Sl. No. | Bug_id | Type | Bug_description | Priority | Status | Comments
1 | US_011 | Defect | Able to edit Role and coach name, but change does not reflect on profile page. In first place can a user/student be allowed to change his role and coach? | P2 |  | Do not have editable fields
2 | US_012 | Defect | Clicking on profile tab - encounter URL http://talentify.in:3000/users/profile/43/false. URL structuring needs to be looked into, does not seem to comply to normal/standard conventions. | P2
3 | HR_001 |  | http://talentify.in:3000/hr_admin/dashboard - Yearly tab on hover, hand highlight not shown | P2
4 | EV_005 |  | The trainers list shud not have horizontal scrolling, instead have previous and next buttons for better usability. | P2
5 | EV_006 |  | Notify users does not update the events page | P1 | Fixed
6 | EV_007 |  | Notify users also sends mail but in mail - "Please click the below RSVP link to confirm your participation. http://talentify.in:3000/rsvp/43/1." it is not a hyperlink. Hitting the above url says "Thanks for confirming ...." even if the user is not logged in, is this the intended behavior.
7 | REP_001 |  | Most of the links do not work. | P1

## 1-Sep
Sl. No. | Bug_id | Type | Bug_description | Priority | Status | Comments
1 | CA_006 | Defect | Delete functionality not working. | P2
2 | CA_007 | Defect | Submit buttons not present in Edit & Create skill pages. | P2
3 | CA_008 | Defect | In some pages we see "© LePo 2014" displayed twice at the bottom of the page. | P1 |  | Will fix, if I encounter again! Since it is content admin, not important for now
4 | CA_009 | Defect | Edit Answers does not work as intended, one cannot edit the answer text. | P2
5 | HR_002 | Defect | When creating an event Add user does not work in the same flow. | P1/P2
6 | US_013 | Defect | Coach field does not display value in user profile page. Create user using admin and coach field was updated there. | P1
7 | US_014 | Defect | Submit button does not work in Tests module | P1 | Fixed
9 | US_016 | Defect | In launch module, clicking on Next get message "No tests available…" even though we have tests assigned to that user. |  | Fixed
10 | EV_017 | Enhancement | Need to display all div's in the same view with no need of scrolling to see the Jobs div | P2
11 | EV_018 | Defect | tester1 , clicking on "Events" tab crashes the application. | P1
12 | COA_001 | Defect | Coach module is not updated with User request today. | P1 | Fixed
13 | COA_002 | Enhancement | Reschedule should have notes | P3
14 | COA_003 | Defect | Reschedule has not sent mail to user fronm coach module. | P3

## 2-Sep
Sl. No. | Bug_id | Type | Time estimate | Bug_description | Priority | Status | Comments
1 | CA_010 | Enhancement |  | When creating content, Add test flow needs test to already have been created. | P2 |  | This flow is yet to be created.
2 | CA_011 | Defect |  | Content Test addition - Add test - Auto suggest is not working/implemented | P2
3 | CA_012 | Defect |  | Content Test addition - Add test - No validations when wrong test name given | P2
4 | CA_013 | Enhancement |  | Content Test addition - Add test - Clicking on view opens test page, instead will be good to have an overlay. | P2
5 | CA_014 | To Do |  | Only Content Test is enabled, Module and skill test not implemented currently. | P2
6 | HR_003 | Enhancement |  | When clicking on View Skill one should be able to view the skill details also. Currently only skill name is shown. | P2
7 | HR_004 | Defect | 2 | When coach rating is null/not rated, hr_admin cannot login to iLabs. | P1
8 | HR_005 | Enhancement | 2 | Create user fields has to be contextual and not general. So for a trainer the fields displayed should be different from that displayed to user, coach etc. Also permission field has to be on top, based on the selection, the relevant fields have to be displayed. | P2
9 | HR_006 | Enhancement |  | Currently HR_admin does not know if a user has already taken a test. | P2
10 | HR_007 | Enhancement |  | Filter results works on OR condition, so if one chooses both "Skill" and "Role" then the results displayed will be of the dropdown highlighted | P1/P2
| HR_008 | Defect |  | Once a filter is set, one is not able to refresh to see the entire list. i.e filter cannot be undone. | P1/P2
11 | COA_004 | Defect | 1 | 1 request by User shows up as 3 requests on the Coach's dashboard. | P1
12 | REP_002 | Enhancement |  | Good to have date displayed rather than just Month | P2
13 | REP_003 | Defect | 0.1 | When user fails test, the text displayed needs to to change, "…..you have answered x out of y correctly. | P1
14 | REP_004 | Defect |  | Skills reports - Time to answer currently shown in mins, good to have in seconds, else we will be showing 40 secs as 1 min, 1 min 30 secs as 2 mins etc. | P1
15 | REP_005 | Defect | 0.1 | Question text - Feedback field has to be renamed to something more meaningful as it comes from "What answer indicates" field. | P1
16 | REP_006 | Defect |  | When different "Skill" clicked only Test results container/div collapses but previous skills "question…" container/div is still open. | P1
17 | REP_007 | Defect | 1 | For a user who passes the test, on the Reports card page get to see "null" displayed below the "Result : Pass" field. | P1
18 | US_017 | Enhancement |  | Module dimensions are fixed, when PDF is uploaded, no provision to maximize it. | P1
19 | US_018 | Defect | 1 | When ordering of skill matrix changes the image of the skill matrix does not change. | P2
20 | EV_019 | Defect | 1 | Take Tests - The Timer on the tests is not working. | P1
21 | EV_020 | Defect | 1 | Take Tests - There is no numbering for the questions. | P1
22 | EV_021 | Defect |  | After test is completed and result displayed, the page does not refresh and Take Test is still displayed on the Events page. | P2
Tests
23 |  | Enhancement |  | What happens when system crashes mid-way during test, how is the session handled then. | P2
24 |  | Enhancement |  | Any provision of pausing test, eg-: student taking test on mobile and suddendly gets a call, he should be able to pause the test | P2

## 3-Sep
Sl. No. | Bug_id | Type | Bug_description | Priority | Status | Comments
1 |  |  |  | P3
| CA | Enhancement | Table display is not full in FF | P3
|  | Defect | Update question is not working, changed Type from Single to MCQ. | P3
|  | Defect | When creating question, the "type" choosen was "MCQ (Single)" but after saving Question I see the type displayed as "Single". The option chosen was "Content Specific". | P3
|  | Defect | Also it does not retain score and option details. | P3
|  | Enhancement | No Spell check help in the text boxes.
| HR | Defect | Company L&D - Test Analytics module - Y-Axis says "Rating" whereas it should be "No. of users". | P1
|  | Enhancement | When I click on a Test, it will be good to have test details like Date, etc | P1
|  | Enhancement | Also good to have same color coding as implemented in the graph, like passed test is green. | P3
|  | Enhancement | For passed and failed candidates good to have scores displayed | P1
|  | Enhancement | Also when one clicks on the test in the ensuing message box, we should have the Test name mentioned. Currently it just shows the user names, if we have numerous tests then HR/Manager will be confussed which test he clicked on. | P1
|  | Defect | In the section "No. of users who have completed all modules" one does not see all the modules displayed. For example during testing we have "Software Testing and Selenium" modules, those do not show up in the section. Also assume we are showing skills, so naming has to change accordingly. | P2
|  | Defect | Also if it "No. of users who have completed all modules" then why are we showing the modules in the X-Axis, it would better we show Week/ monthly wise stats. So date range/frequency should be there in the X-axis
|  | Defect | Encoding issue with "L&D" being displayed as "L&amp;D" | P1
|  | Enhancement | For "No. of users improving on skills" it would be good to have the number as a hyperlink and when one clicks on the number, one should be able to see the user lists. This will help HR/Manager get a quick overview of the users who need to improve. | P2
|  | Defect | Company L&D - "No. of users who have completed all modules" module - Y-Axis says "Rating" whereas it should be "No. of users". |  | Fixed
|  | Defect | When one changes the month just the Login section changes, the other sections like "Test Analytics" does not show the month data. For example I see Sep data when I choose Aug month. | P3
|  | Defect | Yearly login activity, graph looks wrong - Sep did we have 100+ users login in? | P2
Is it unique login or everytime a user logs in, we increment the counter?
|  | Defect | Graph says Second quarter "No. of logins" as 47 but graph there is no display of it. | P1
|  | Enhancement | Employee Stats module - One should be able to search by employee ID (Unique key) since names can be same. Now we are searching by username which is still fine, since even it should be unique, provided we are doing a duplicacy check when we create user names. | P2
|  | Enhancement | There is no auto suggest. | P2
|  | Defect | If wrong name is given no user message displayed, or any error message | P2
|  | Defect | When one creates a dupe user, system does not throw error message. Dupe user though is not be displayed in the list view of users. | P2
|  | Defect | "Track an Employee's Competency Development" Module - Clicking on a skill breaks the skill reports module. Similarily clicking on notes also does not display the intended notes. | P1
|  | Defect | User Analytics section is blank. | P1 |  | Needs to be removed
|  | Enhancement | Role - Heading "Action should be centered and not left-aligned. | P1
|  | Defect | Events - When Trainer accepts event we get a hyperlink in the text -" Trainer Accepted INVITE". And when one hovers over INVITE, an ad is displayed.
US
|  | Defect | User has taken test yesterday but still it shows up in his events page. It should not show up. | P2
|  |  | Events - Clicking on "RSVP" takes one to next tab, ideally it should happen on the same page. | P2
Also should meeting be categorized under Classes?
|  |  | Clicking on "RSVP Yes" does nothing. | P2
Issues found post Bug triage
Create Role - the time taken > 5 secs to load the page.
New enrollment form flow, if an existing test is assigned to a new user, we encounter the message -"You have already taken this test." This should not happen coz the user is new and would not have taken the test.
Map skills page , Links like "View" & "delete" not working.
| College User |  | College User - Launch new module label is misaligned.
Clicking on Report card redirects to login page, but application does not crash. Happens with all the links like Profile, Events etc. and also with "Launch new model" link.

## 4-Sep
Sl. No. | Bug_id | Type | Bug_description | Priority | Status | Comments | QA Comments
ADMIN
|  | Enhancement | List Organizations - When one chooses this option, the page displayed has title as "Company List". Now that we are having both Corporate and College clubbed together, this name has to change to something more meaningful and descriptive of both Company & college. |  |  | This is a 'to-do'. Contextual view will be implemented
|  | Defect | Trying to upload a csv file crashes the application. | P1 |  | CSV upload needs a pre-defined format. We had agreed on you testing this part, only after I get back!
|  | Defect | The skill module flow stops at 1st module itself, there is no next button to move to next module. Steps to repro -: - Navigate to "Skill Review" page - Click on Play on 1st module in the list. - The module opens but the window has just close button and no next or finish action once the module is read. - Even after one closes and comes back to "Skill Review" page, the focus is still on module 1 and 2nd module is disabled. |  |  | To advance to the next module/content, you have to click on 'Play Next'. Clicking on 'Review' button, only lets you view older content and doesn't advance. | Could also be due to a doc file upload for the 2nd module.
| PRINCIPAL | Defect | Not able to Edit an user. Realized I had given a wrong role (B.Com I) when submitting and needed to change the role to (B.Com II), but not able to. |  |  | Needs to be fixed.
|  | Defect | When we try to delete an user(like College User1, College User2), it crashes the application. | P1 |  | Delete's aren't working anywhere, and need to be avoided.
|  | Defect | Principal is seeing the HR admin view of Company L&D stats. This brings us back to the need for Contextual view implementation. |  |  | This is a 'to-do'. Contextual view will be implemented
|  | Defect | Same issue as yesterday on Employee stats page, clicking on a skill breaks "Click on a skill to know more…" module. |  |  | Needs to be fixed.
|  | Defect | Many questions that were tagged, had a type as MCQ(Single Answer) have all changed to having no Tags and Type as Single. | P1
| Adding Tests as content admin | Enhancement | Create questions form needs to have vertical scrolling.
|  | Defect | In Answer created window, even though I have entered "What answer indicates" in create Answers, still it shows up as "-".
|  | Question | For a Event of Type "Test" why do we need Trainer to be invited? |  |  | This is contextual. When you select an Event of type 'Test', the 'Invite Trainer' tab disappears, and 'Select Test' tab appears.
|  | Defect | In Event List page, clicking on "View/Edit users" one is navigated to Edit event page, flow is not logical. Instead user should be navigated to "User list" section of the same page.
| USER | Enhancement | When question is too long, alignment of question goes to next line.
|  | Defect | Even if the User fails the test, one still gets to see the message -"You have successfully completed the test". |  |  | Steps to reproduce this? We need to discuss. Is this an event test or content test? | It is the pre-test which is scheduled as an event by the Principal.
|  | Enhancement | When user logs in first time and "Complet your Profile", he is correctly navigated to Enrollment tab, but he cannot see his personal profile, even if he clicks on it. One should be able to see the personal profile, before enrollment. |  |  | Needs to be fixed.
|  | Defect | When no pre-test created for a role and user, still one gets to see "Take a test" and when one clicks on it, we see an empty window with title "Coach session". | P1 |  | Needs to be fixed. It should load google form test.
|  | Defect | Since test cannot be taken, user is not able to finish the flow and hence he is stuck. | P1 |  | Needs to be fixed.
|  | Defect | When User does not complete test within the stipulated time, his report card displays "No tests results available", when actually the user was displayed with the message "You have failed….". Along with the test score 2/10 | P1 |  | Needs to be fixed.
| Home page | Enhancement | Good to have Notice Boards concept that displays events, any announcements, pin-ups, circulars etc.
|  | Enhancement | Forums is a very much required feature, so that students and coaches/trainers can discuss any topic
|  | Enhancement | User/Students homepage - Max test score, average test score can be displayed so that students know where they are relatively to others.
|  | Enhancement | Fun concept is good to have, a la "Adda" sorts, so that students can share some light moments. This can be moderated else it can become a nuisance.

## 5-Sep
Sl. No. | Bug_id | Type | Bug_description | Priority | Status | Comments
| USER | Question | Enrollment form are so many fields needed, it is cumbersome to fill.
|  | Defect | Timer is timing out very fast, has minutes been changed to secs by any chance. I had a test for 5 minutes but it timed out within 5 secs. | P1
|  | Defect | Clicking on a Meeting "Join" button leads to Zoom wherein one encounters "Invalid Meeting ID" message.
|  | Question | Do event tests not show up in Report card.
|  | Question | In evening Submit button in "Request meeting with coach" went in an infinite loop without completing the action.
| COACH | Enhancement | The Coach Dashboard page -: http://talentify.in:9000/coach/dashboard/ needs better alignment of the text and sorting of events chronologically datewise.
|  | Defect | The user view has hyperlinks on the user name but clicking on it does nothing.
| Content Admin | Defect | Navigate to Content page. - Click on View/Edit content - Click on "Add Test" It navigates back to login page.
|  | Defect | Wanted to update one more module to a skill but not able to Add module in the Edit skill section.
HR_Admin
|  | Defect | See negative value under "No. of users who have not taken the test".
|  | Defect | In the tests window, See 1 or 2 users under "Tests Taken" but they not being there under "All". From where are we querying All users list from and Tests Taken from |  |  | Looks like college flow pre-test user shows up in "Tests Taken" but will not show up under "All".
|  | Enhancement | Would like to see Active and inactive users stats.
|  | Enhancement | Would like to see clear differentiation/bordering between the different Tests.

## 8-Sep
Sl. No. | Bug_id | Type | Bug_description | Priority | Status | Comments
1 | REP |  | Does it only take values from content tests and not event tests
On small screen, "Click on a skill" and "Click on a question…" go below the default screen resolution, hence not visible by default and hence would be good if we can show that module also aside the "Notes" and "Coach rating".
Normally in such cases, except for 1st module, other modules will be collapsed so as to save on the real estate of the site. Else only a few modules will be shown and others though present in the page do not show up in default view.
| COACH |  | When notes is descriptive and long it spills over the display text area. |  |  | User - Coach
Hyperlinks/weblinks show up as plain text in notes.
| REP |  | In the reports page, do not get to see the full notes entered by coach |  |  | Auto 2 user
The hand does not appear on top of next and previous buttons.
| COACH |  | Coach dashboard page - no vertical scrollbar for the page.
There is no rating scale to help with scoring.
Also currently Coach cannot figure out clashes in appointment requests. If multiple students opt for same time then there is a clash. Further it will be good if coach can figure out if the multiple requests are on the same subject, then he can accept all and if not then he can reject.
When Coach changes the Skill of an user no notification of the same to the user. Only that the skill change shows up in the Gym page and Reports card page.
Coach rating display - On changing the skill and changing the rating, I get to see both the ratings, one where the rating scale was at the time of changing the rating and the changed rating.
|  |  | The changed skill matrix shows up but the modules of the skill does not play/show up |  |  | User - tester6, skill - Selenium
| REP |  | For user "Auto1" Coach notes do not show up in Report page but show up in Coach's dashboard page
Also Coach rating history, if Coach rates twice in the same month, looks odd, better to have date in place.
When there is no "Notes" and "Coach rating" good to display text saying the same like "No Notes available" …so no value have default text "No notes/Rating available" /"Coach has not provided notes/Coach has not yet rated".
|  |  | Question text field - there is text overflow. |  |  | User - Student1
| TEST |  | Today test name not showing up in the test module.
Only pre-test results shows up in Report Card page, event test does not show up.
| PROFILE |  | Certain flows lead to display of wrong personal profile details. Steps to repro -: 1) Navigate to Profile page of "Student 2". 2) Click on Enrollment Form. 3) Navigate back to "Profile" page. We can see the profile details of "College User 1" show up.

## 10-Sep
Sl. No. | Bug_id | Type | Bug_description | Priority | Status | Comments
|  | Defect | Trying to delete user crashes the application. |  |  | http://talentify.in:9000/users/list
When system crashes/breaks good to have a custom 404 page with some appropriate error messages.
| Hr_Admin/Princ |  | Currently hr_admin & Principal are able to see all users details, i.e Principal can see Corporate user details. Filtering to be implemented.
|  |  | See untitled module in the bottom of the page. |  |  | http://talentify.in:9000/hr_admin/dashboard
| Principal |  | Logged in as Principal but page URL displayed as "http://talentify.in:9000/hr_admin/dashboard#".
Test Analytics shows up corporate details also for Principal log-in
Report Card has test details under User page, but same does not show up in Student Stats page. Clicking on the skill displays "No test results available".
User information section still displays "Role" and not "Batch".
When one clicks on "Create user" the heading title tabs change back to hr_admin one, like "Company L&D Stats", "Employee stats".
Batches - It should say "Create new Batch" and not "Create New Role". Also heading to change to "Batch List" and not "Role List".
| Hr_Admin |  | Good to have close (collapse) button for Coach rating, Notes etc
| User |  | For existing role, when new skill is added, it crashes |  | Fixed
| TEST |  | When user fails test, reason field shows up as null.

## 11-Sep
Sl. No. | Bug_id | Type | Bug_description | Priority | Status | Comments
|  | Enhancement | There is no provision to delete uploaded content. Use case - I figured out I had uploaded the first part of the content instead of the second and want it to be removed.
File Upload
|  | Defect | There is no check for the file type. I tried uploading a .rar file and it threw a message, open file with. Either ways defect, it should not allow .rar type files and if you still allow, then we should not get that "Open with…." pop-up.
Tried uploading a 15 MB ppt, did not go thru. Same behavior as above, encountering "Open file with….." after sometime (around 2 mins…).
Xls with macros upload also fails and has the above behavior. So is the case with word (docx) and txt files. Also when the files are huge, it takes time for the pop-up box (Open with…) to appear.
Except for pdf all other file types seems to display the above behavior
Took 4 mins to upload a pdf file of size 17.8 MB
Supports Hindi. L10n check
RECRUITER
User list does not show up initially. Steps to repro -: 1) Provide Job details, and then Submit. 2) On the ensuing page, in User List section do not get to see any users. 3) Only on entering "Interview Round" do the list of users show up.
After filtering users, when I select one user, page reloads and the entire user list is again shown. The filtered list should show up instead.
|  |  | Once a User "Applies" for the job, clicking on View/Edit job crashes the application. | P1 |  | /root/lepo-test/controllers/recruiter.js:55 eport.find({ where: ['"UserId" = ? AND "TestId" = ?', c.id, stepTest.TestId]}) ^ TypeError: Cannot read property 'TestId' of null at null.<anonymous> (/root/lepo-test/controllers/recruiter.js:55:86)
|  |  | When description is too long, application crashes. | P1 |  | events.js:72 throw er; // Unhandled 'error' event ^ error: value too long for type character varying(255) at Connection.parseE (/root/lepo-test/node_modules/pg/lib/connection.js:561:11)
Interview Rounds module, the link "Add/Edit interview" is disabled.
|  | USERS - Jobs | Jobs - if the description is too long it overlaps with Apply button. Better to have more link.
Good to have provision for Company logo along with the Job Ad.
There is no provision for a detailed JD. If JD is detailed then user/candidate should have provision to download the JD.
Just get to see Job description, do not get to see other details like Location, Salary etc.
Once user clicks on Apply it says "Thank you for applying to this job. Please answer the test." even when there is no test. It was an Interview event type.
After user applies for Job. When he revisits the events page, it says "There are no relevant jobs for you.". Instead it should be "Applied for xyz job". Coz if there are many jobs then how does the candidate know which all jobs he has applied for.
Non-functional issues
Accessibility
Talentify Home-page Login
|  | Defect | There is missing alt text for the Logo.
|  | Defect | Username & pwd, the form labels are empty.
|  | Defect | Page has document language missing.
|  | Good to have fix | There is no h1 heading for the page.

## User-flow
Sl. No. | Observation | Comments
COLLEGE SCENARIOS
1 | In the Explorer section see- "She is invited to take a psychometric test and fill out her profile and indicates her career interests. She then sees customized content "…… currently Principal assigns roles and maps skills & then creates the User. Does that mean Principal already has the student details.
2 | "She sees that there are several good colleges offering courses in finance.", where does one get to see this college list in the application.
Principal at Admission time
"She is responsible for ensuring that enrollments for the incoming batches are up to capacity", is there any provision in the application to set that limit and automation validation when that limit is reached, so that Principal does not create any further users.
"accesses the platform and can see students who have applied to her college and shortlists them based on various criteria" …..One of the criteria will be Test marks, currently one does not get to see the Users listed based on marks. Filters?
USABILITY
Identity | Logo - good to have it on the top left section of the page and on clicking it on any page should navigate one back to homepage.
Homepage - should have content that are digestible in 5secs on what is the gist of the site.
About Us - About iLabs and other details of company that is public.
Contact Us - For people to know the contact folks for business etc.
Navigation | Site Search should be easy to access.
Good to have caching enabled.
Events Page
Good to have calendar and the events color coded on the calendar. For example Appointments as 1 color, Tests one more color etc.

## Sriram-bugs
Sl. No. | Bug_id | Type | Bug_description | Priority | Status | Comments
Sep 4th
One picture for MS Word mysteriously disappeared from the view in user kifkid1 - not sure what happened to cause it.
The images seem to be getting displayed in various pixel sizes, in turn causing misalignment of the text below. Again seems to be a new issue? Perhaps a spillover of effect #1.

## Open-P1's
Sl. No. | Bug_id | Type | Time Estimate | Bug_description | Priority | Status | Comments
1 | US_003 | Defect | 1 | Gym- Text and images to also be hyperlinks | P1
2 | US_007 | Enhancement | 1 | need other modules and placeholders in the page like motivators, stars, an overall performance indicator etc. | P0 |  | Pie chart with peer percentile in the center. Add modules completed in a table below the skills for now.
4 | AD_003 | Defect | 0.1 | No submit button in edit skill page | P1 |  | contentadmin
6 | CA_002 | Defect | 0.1 | Description field needs to be added in Upload content | P1
7 | CA_003 | Defect | 2 | drop-down for add test in content admin for edit content. | P1 |  | Convert to drop-down
8 | MAIL_001 | Enhancement | 2 | New user creation - in email text link(http://talentify.in:3000.) has to be a hyperlink, needs to be handled. | P1 |  | Convert lePo to Ilab in the email text
9 | REP_001 |  | 2 | Most of the links do not work. | P1
10 | CA_008 | Defect | 2 | In some pages we see "© LePo 2014" displayed twice at the bottom of the page. | P1
11 | US_013 | Defect | 1 | Coach field does not display value in user profile page. Create user using admin and coach field was updated there. | P1
12 | EV_018 | Defect | 2 | tester1 , clicking on "Events" tab crashes the application. | P1
16 | REP_004 | Defect | 2 | Skills reports - Time to answer currently shown in mins, good to have in seconds, else we will be showing 40 secs as 1 min, 1 min 30 secs as 2 mins etc. | P1
18 | REP_006 | Defect | 2 | When different "Skill" clicked only Test results container/div collapses but previous skills "question…" container/div is still open. | P1
20 | US_017 | Enhancement | 1 | Module dimensions are fixed, when PDF is uploaded, no provision to maximize it. | P1
21 | EV_019 | Defect | 1 | Take Tests - The Timer on the tests is not working. | P1 | Fixed Partially | Timer now works but it ticks faster than the time. I have a bug mentioned for this in 5-Sep worksheet.
22 | EV_020 | Defect | 1 | Take Tests - There is no numbering for the questions. | P1
24 | HR_010 | Enhancement | 1 | When I click on a Test, it will be good to have test details like Date, etc | P1 |  | We don't have these details, for now
27 |  | Defect | 1 | Encoding issue with "L&D" being displayed as "L&amp;D" | P1
28 |  | Defect | 1 | Graph says Second quarter "No. of logins" as 47 but graph there is no display of it. | P1 |  | Not a bug
29 |  | Defect | 1 | "Track an Employee's Competency Development" Module - Clicking on a skill breaks the skill reports module. Similarily clicking on notes also does not display the intended notes. | P1
32 | CA_001 | Defect | 2 | Labels while uploading content needs to be thr | P1/P2
33 | MISC_002 | Enhancement | 3 | Date and time field needs to be validated and date picker needs to be implemented. | P1/P2
34 | MISC_003 | Enhancement | 1 | Sorting needs to be implemented across the application in List view. | P1/P2
35 | HR_002 | Defect | 2 | When creating an event Add user does not work in the same flow. | P1/P2
New List
|  | Defect |  | Trying to upload a csv file crashes the application. | P1 |  | CSV upload needs a pre-defined format.
| PRINCIPAL | Defect |  | Not able to Edit an user. Realized I had given a wrong role (B.Com I) when submitting and needed to change the role to (B.Com II), but not able to. | P1 |  | Needs to be fixed.
|  | Defect |  | When we try to delete an user(like College User1, College User2), it crashes the application. | P1 |  | Delete's aren't working anywhere, and need to be avoided.
|  | Defect |  | Same issue as yesterday on Employee stats page, clicking on a skill breaks "Click on a skill to know more…" module. | P1 |  | Needs to be fixed.
|  | Defect |  | Many questions that were tagged, had a type as MCQ(Single Answer) have all changed to having no Tags and Type as Single. | P1
| USER | Defect |  | Even if the User fails the test, one still gets to see the message -"You have successfully completed the test". | P1 |  | Steps to reproduce this? We need to discuss. Is this an event test or content test?
|  | Defect |  | When no pre-test created for a role and user, still one gets to see "Take a test" and when one clicks on it, we see an empty window with title "Coach session". | P1 |  | Needs to be fixed. It should load google form test.
|  | Defect |  | Since test cannot be taken, user is not able to finish the flow and hence he is stuck. | P1 |  | Needs to be fixed.
|  | Defect |  | When User does not complete test within the stipulated time, his report card displays "No tests results available", when actually the user was displayed with the message "You have failed….". Along with the test score 2/10 | P1 |  | Needs to be fixed.
|  | Defect |  | Timer is timing out very fast, has minutes been changed to secs by any chance. I had a test for 5 minutes but it timed out within 5 secs. | P1
| HR_Admin | Defect |  | See negative value under "No. of users who have not taken the test". | P1
|  | Defect |  | In the tests window, See 1 or 2 users under "Tests Taken" but they not being there under "All". From where are we querying All users list from and Tests Taken from | P1
| COACH | Defect |  | When notes is descriptive and long it spills over the display text area. | P1
|  | Defect |  | Hyperlinks/weblinks show up as plain text in notes. | P1
|  | Defect |  | When Coach changes the Skill of an user the changed skill matrix shows up but the modules of the skill does not play/show up. | P1
|  | Defect |  | For user "Auto1" Coach notes do not show up in Report page but show up in Coach's dashboard page | P1
| PROFILE | Defect |  | Certain flows lead to display of wrong personal profile details. Steps to repro -: 1) Navigate to Profile page of "Student 2". 2) Click on Enrollment Form. 3) Navigate back to "Profile" page. We can see the profile details of "College User 1" show up. | P1
| PRINCIPAL |  |  | Trying to delete user crashes the application. | P1
|  |  |  | Currently hr_admin & Principal are able to see all users details, i.e Principal can see Corporate user details. Filtering to be implemented. | P1
|  |  |  | Report Card has test details under User page, but same does not show up in Student Stats page. Clicking on the skill displays "No test results available". | P1
|  |  |  | When one clicks on "Create user" the heading title tabs change back to hr_admin one, like "Company L&D Stats", "Employee stats". | P1